Project Overview
The Deerfield Beach Housing Authority is seeking qualified, licensed general contractors to submit proposals for converting an existing single-family four-bedroom unit into two self-contained apartments (Unit A and Unit B), in compliance with NSPIRE standards.
This property will serve as emergency housing for working individuals and families who do not qualify for vouchers but cannot afford market rent. The conversion is part of a broader initiative to expand affordable transitional housing in the community.
Scope of Work
1. Architectural & Permitting
- Prepare architectural/engineering drawings for permit submission.
- Ensure compliance with fire, structural, and zoning codes.
- Secure all necessary permits for structural, electrical, and plumbing.
2. Partition Wall Construction
- Construct a partition wall to divide the existing space per attached drawings.
- Include a framed doorway in the wall for future reconfiguration to single-family if needed.
3. Kitchen Construction
- Construct a second kitchen (Unit B).
- Install new appliances and cabinetry in Unit B kitchen.
4. HVAC
- A shared HVAC system will serve both units.
- Install a Nest tamper-proof thermostat in a neutral/common area.
- Propose options for improving individual comfort (e.g., ceiling fans, zoning dampers).
- Ensure all ductwork and returns are balanced for even airflow.
5. Electrical & Plumbing
- Maintain single metering for electricity and water (agency will pay utilities).
- Modify plumbing and electrical as needed for the new kitchen and bathroom layout.
- Ensure all outlets are GFCI-protected within 6 ft of water source.
6. Laundry Area
- Shared laundry area to be outfitted with stacked washer/dryer (piggyback style).
- Provide secure, shared access through side entrance.
- Close off interior access from kitchen.
7. Walkway & Access
- Create a gravel walkway with borders for side entrance access.
- Flag accessibility concerns and suggest alternate surfacing if needed.
8. Structural Repairs
- Repair rusted/deteriorated carport columns.
- Ensure all structural work meets local code and safety standards.
9. Windows & Doors
- Repair existing windows where feasible.
- Provide a separate line item for replacing with impact-rated windows (preferred).
- Verify that all bedrooms have proper egress.
10. Paint & Finishes
- Interior and exterior paint throughout to meet NSPIRE requirements.
- Units must be delivered fully make-ready: clean, safe, and code-compliant.
11. Gas to Electric Conversion
Eliminate gas lines; convert all appliances and systems to electric.

Deliverables
- Architectural and engineering drawings
- Proof of permitting
- Detailed construction schedule
- Materials and appliance specifications
- Cost breakdown for labor and materials (including alt. pricing for window replacement)
- Certificate of Insurance and license

Additional Notes
- NSPIRE compliance is mandatory for final inspection.
- Contractor will coordinate directly with DBHA representatives for access and walkthroughs.
- All work must meet safety, code, and quality standards expected for publicly funded housing.